## Architectural Decisions
ID | Subject | Issue / Requirement | Decision | Rationale
G01 | Cost Efficiency | GCP projects managed independently by departments risk duplicated services, inefficient spending, and lack of consolidated cost tracking. Require cost allocation, tagging strategies, and budget control mechanisms. | Implement GCP Resource Hierarchy with centralized billing account and per-department projects. Enable cost tracking using labels and cost controls with Budget and Alert policies. | Allows cost visibility, optimization, and billing transparency across departments while preserving autonomy.
G02 | Security & Compliance | Managing IAM policies and compliance for regulated workloads (e.g., Kronos with PII) requires centralized controls and monitoring. Departments need flexibility without compromising governance. | Use GCP Organization policies and IAM Conditions with central logging via Cloud Audit Logs and SCC. | Provides centralized control, fine-grained permissions, and compliance visibility for sensitive workloads.
G03 | Workload Isolation | Departments require isolated compute and network environments for development, testing, and production. Need to enforce environment separation while allowing shared service access. | Use GCP folders and projects per environment per department with Shared VPC and Service Perimeters. | Enables secure, scalable, and isolated environments with controlled interconnectivity.
G04 | Operational Efficiency | Manual environment setup causes inconsistency and delays. Require automated provisioning, consistency, and drift detection. | Adopt Terraform with CI/CD pipelines, standard modules, and policies-as-code using OPA or Forseti. | Delivers automation, compliance, and reduced operational effort across multi-team environments.
G05 | Networking and Connectivity | Need centralized control over VPN, DNS, and NAT services while enabling scalable interconnectivity. | Implement hub-and-spoke networking with Shared VPC in the hub and spoke VPCs per department. | Reduces network complexity and centralizes control, monitoring, and security.

## Use Case Summary
ID | Use Case Name | Scenario | Process Description | Devices | Design Notes
GUC01 | Business Analytics & Reporting | Allows teams to create reports and dashboards using BigQuery and Looker for enterprise-wide analytics. | Users can access Looker Studio or Looker dashboards from browsers, connecting to BigQuery datasets and other sources for dynamic analytics. | From personal machine / GCP-managed device | Secured using IAM and VPC-SC
GUC02 | HR System – Kronos | Supports delivery of secure HCM services for HR and payroll operations. | Kronos deployed in GCP ensures compliance with data protection laws, high availability, and fine-grained access control through IAM and VPC-SC. | From HR-managed machines / remote access devices | IAM Conditions + Org Policies enforced for HR data
GUC03 | Machine Learning Platform – Doc AI | Provides an experimentation platform for ML engineers to develop document intelligence solutions. | Google Cloud Vertex AI enables training, versioning, and deploying ML models on secured isolated projects. GCS and BigQuery are used for data storage and analytics. | From authorized workstations / remote ML notebooks | Isolated project with limited outbound access
GUC04 | Enterprise Finance Platform | Supports budgeting, forecasting, and financial analytics for business units. | Finance applications leverage BigQuery for reporting, Pub/Sub for data ingestion, and Dataflow for ETL pipelines in a scalable, secure environment. | From finance department systems / secured cloud access | Data classification and encryption enforced

## RAID Log
ID | R/A/I/D | Description | Impact | Resolution Plan | Raised By | Resolution Owner
01 | R | Migration Risks: Downtime, data loss, or configuration errors during GCP project onboarding | Potential service disruption and data integrity loss | Use Deployment Manager or Terraform with automated backups and staged environment migration | Cloud Infra Team | GCP Migration Lead
02 | R | Security Risks: Misconfigured IAM policies or lack of VPC Service Controls | Potential data exposure or unauthorized access | Enforce IAM Recommender, VPC-SC, and SCC alerts; conduct quarterly security posture reviews | Security Architect | Cloud Security Team
03 | R | Operational Risks: Resistance to change or lack of stakeholder buy-in for GCP transition | Delays in adoption, shadow IT, and fragmented cloud management | Conduct executive briefings and cost-benefit analysis; initiate change management workshops | IT Strategy Team | Cloud Governance Lead